# Museums readiness checklist for Local Government Reorganisation (LGR)

Arts Council England

Published: June 2026

Contents

Introduction	3

How to use this checklist	3

Checklist	4

Action #1: Be part of the planning process	4

Action #2: Carry out a Service Data Audit	6

Action #3: Identify risks	7

Action #4: Manage change (workforce support)	8

Action #5: Manage change (stakeholder relationships)	9

Action #6: Advocacy	10

Action #7: Compliance with external standards	12

Action #8: Plan for the future / museum specifics	12

Action #9: Get support	13

Action #10: Support for museums who are not operated by a local authority	15

# Introduction

This checklist is designed to help local authority owned and operated museums ready themselves for the challenges and opportunities around the current (2026 - 2028) programme of Local Government Reorganisation (LGR) in England.

Action 10 of the checklist is for independent museums and local authority reliant museums to use to prepare for local government reorganisation. Arts Council England defines local authority reliant museums as ‘if the local authority were to withdraw its support or provision it would significantly impact on the museum's ability to deliver its current operations.’

## How to use this checklist

It is suggested that senior leaders in local authority owned and operated museums review the checklist and work with colleagues to compile the information that will assist in promoting understanding of the service operation, risks and responsibilities and its value. This will be essential for future service planning in new authority structures.

Independent and local authority reliant museums are recommended to review and complete the additional checklist (Action #10) to enable them to advocate effectively for their services and future support in the new local government operating environments.

The information you collate will need to be reviewed and updated throughout the LGR planning process and beyond vesting day.

# Checklist

## Action #1: Be part of the planning process

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Internal – within your authority Ensure museums are represented and your voice is heard in the LGR planning teams within your current local authority. Ensure this is also the case within the transition teams planning for the new authorities. | Internal: Museums will have a lower profile than larger statutory services, so your priority is to proactively ensure that they are considered in the planning process – their value is understood and risks / legal obligations are not overlooked. Museums may previously have operated under authorities that were not responsible for major statutory service areas such as adult social care, children's services, or highways. Gaining insight into how your museums relate to these areas and can work alongside them will be essential. The value and potential of museums will not necessarily be recognised initially by the officers and shadow elected members you will be working with. Understand the strategic objectives of the new authority and align the museum’s offer to optimise synergies. Identify the colleagues who can champion your services. |  |  |
| Internal – within your authority Align your service clearly to one of the new workstreams that will be established to reflect the structure of the new authority. |  |  |  |
| External – museums colleagues Talk to neighbouring museum services who are also part of the change in your area. You can start the conversations before decisions are made, but ensure you start them once the future local authority boundaries are known. | Ensure you all carry out the data audit (see below) so you can compare your services / commitments / strengths / risks. Network with colleagues through local support forums, special interest groups, conferences. |  |  |
| Utilise Museum Development support -(which may have access to different channels) | MD may be involved in relevant conversations at a different level. MD will run briefings and support sessions. MD will provide opportunities for peer support and networking. |  |  |

## Action #2: Carry out a Service Data Audit

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Collate data so you can quantify the scope, scale, strengths and risks to your service. The audit table covers: - Workforce - Buildings - Service delivery - Finance - External and partnership funding agreements - Contracts - Museum collection - External standards compliance - Risks - Contribution to council strategies and local agenda - Advocacy case studies | See the separate document with suggested questions to answer and an audit table for completion. Carry this out as soon as you can and update as needed. Draw on the Museum Development Annual Museums Survey data where appropriate. Involve colleagues to gather the information. |  |  |

## Action #3: Identify risks

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Use the Service Data Audit to identify risks to the service, as well as opportunities for different ways of working and engagement – include all risks particularly related to LGR. | Risks can be incorporated into formal planning processes or escalated to LGR and senior colleagues to ensure key issues are identified and addressed early. Museums aren’t statutory services, but collections are a long-term commitment and a symbol of public trust (and sometimes have specific legal obligations attached to them). Museums should check whether there is a specific local act / legal structure that needs to be taken into account (e.g. County of Lancashire Act 1984). Are you a place of deposit for archaeological archives in the area? Most LAs provide some level of support to the wider (independent) museum sector, this could be through grants, provision of premises and/or shared services and this should be quantified. |  |  |

## Action #4: Manage change (workforce support)

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Do you have a plan to communicate with staff and volunteers? A regular mechanism for passing on news? Even when there is little to report avoiding a news vacuum is helpful. | Take a planned approach for passing on regular updates to your workforce and offering opportunities to ask questions. Encourage team members to share any experience they have of LGR from elsewhere. Be aware of opportunities to involve colleagues in planning work. |  |  |
| Ensure you have support in place for yourself (as a service manager) | Peer support within your LA, support from MD, sector colleagues. |  |  |

## Action #5: Manage change (stakeholder relationships)

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Do a map of your stakeholders. They will range from your visitors, Friends groups to collection donors, schools and colleges to sponsors and partners in the sector and wider community. Consider what communication is appropriate and useful through this time of change. Be ready to record and flag any key risks (and opportunities) that arise from this process. | This is a piece of work that can be done with colleagues. This will be a long-term process so will need to flex and change as circumstances change. |  |  |

## Action #6: Advocacy

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Advocacy – for your museums service - Have you collated the data from the audit? - Have you accessed any wider impact data (e.g. from the Museum Development Annual Museums Survey/ AIM economic impact assessment / 2024 NMDC/Art Fund survey on how the public value museums - Data around work with key partners including independent museums in your area. | Get your advocacy information together/ready to use. |  |  |
| Internal advocacy – within your existing authority - LGR planning teams - Senior colleagues - Colleagues in allied services | Keep talking / find out what is going on / ensure that museums are not forgotten in the conversations and planning. |  |  |
| Internal advocacy – in the new authority - Be proactive with the transition teams - Ensure that museums are associated with the planning for a specific workstream - Start to build relationships with shadow councillors when they are elected - add to your mailing lists, invite them to events, invite for tours etc. |  |  |  |

## Action #7: Compliance with external standards

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| List and note commitments to / risks around external standards that you work to / have been awarded, for example: - Museum Accreditation - Visitor Attraction Quality Assurance Scheme (VAQAS) - Spectrum | The need to continue to comply with external standards to ensure externally validated high quality services continue to be delivered can be a powerful tool for advocacy. |  |  |

## Action #8: Plan for the future / museum specifics

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Ensure you are up to date and understand the requirements around key compliance, including: - Museums’ specific GDPR and data sharing: This covers collections and user / audience data. Councils will be following the principles advised by the LGA - Safeguarding—ensure museum policies and procedures are understood and maintained - Government Indemnity - Government Indemnity certification should be updated as part of the Local Government Reorganisation process |  |  |  |

## Action #9: Get support

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Are you accessing support for LGR from a variety of sources? - High level: Local Government Association- LGR and Devolution Hub - Sector level: Arts Council England, Museum Development teams - Wider culture: Guidance for Libraries and Archives - Local: Authority colleagues, museum colleagues, forums and networks Sector adjacent bodies including Community Leisure and UK and CLOA (Chief Cultural and Leisure Officers Association) have working groups and support for LGR that may be relevant to your organisation) |  |  |  |

## Action #10: Support for museums who are not operated by a local authority

| Actions | Notes | Responsible | Completed? |
| --- | --- | --- | --- |
| Audit work: - Understand and quantify the support you currently receive - from financial to in kind (e.g. charitable rate relief top up, grants, professional advice) - Make sure you have copies of formal / legal agreements with the LA - e.g. lease agreement, funding agreement - Do you have collection loans to/from the local authority? |  |  |  |
| Advocacy work: - Refresh/refine a clear one-page document which explains what you do, who you are and key impact to share with new stakeholders - Build relationships with shadow elected members once they are in place - Be part of any local planning forums to demonstrate your value - Work with MD to understand and promote the value that your service offers to the local area (use Museum Development Annual Museums Survey data) |  |  |  |
| Contracts with local authorities: - Independent museums may have arrangements in place with local authorities around and including agreements around provision of premises, staff or services - Understand and review the contractual arrangements in place and be prepared for possible updates - Update your risk register to ensure all risks are managed appropriately |  |  |  |